## April 2014
Idara-e-Taleem-o-Aaghai (ITA)
Quarterly Planner (April to June)
2014-04-01
Program/ Project | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Adopt a School and Public Private partnership for school improvement of Public sector schools in Sindh | bar: 1
SASI | Meeting with MD of Punjab Education Foundation (Lahore) | bar: 8
Meeting with Additional Director of Punjab Education Foundation (Rawalpindi) | bar: 9
SASI Impact Evaluation Meeting with Aagahi School System | bar: 8
Project Evaluation by DAI | bar: 7 to 22
SASI School Assessment of Star Fish Foundation | bar: 20 to 30
SASI Market Research
SASI Marketing and Improvement Partnership
ASER | District Launch Peshawar | bar: 2
District Launch Kohat | bar: 4
District Launch Bahawalpur | bar: 1
District Launch Khushab | bar: 4
District Launch Muzaffargarh | bar: 11
District Launch Multan | bar: 22
District Launch Mianwali | bar: 7
Baithaks in Khushab (Gunjial, Mitthatiwana, 39MB) | bar: 28 to 30
Baithaks in Mianwali (Mouch, Pie Khail) | bar: 14; 16
Baithaks in RYK (Bhong Sadiq abad, Wahid Bux , Kotla Ray Qabool, Tajpur Peerwala, Chak 102 -P) | bar: 16; 23 to 25; 30
ASER Dissemination at University (Lahore School Economics ) | bar: 14
ASER Dissemination at LUMS | bar: 25
Journalist's trainings (Hyderabad, Multan, Bahawalpur, Sukkhar, Peshawar, Lahore, Quetta and Karachi) | bar: 1; 3; 9 to 10; 15 to 16; 22; 30
ECE | 2 day Refresher on ECE in Lahore | bar: 2 to 3
Project Orientation of Staff- PPAF (ECD) | bar: 14 to 17
Collection of ECE Books/reading material | bar: 7 to 11
TOT on ECE under DC project | bar: 20 to 23
WSIP | Identification of UCs Villages for DC | bar: 1 to 5
Identification of Volunteers for DC | bar: 26 to 30
Identification & Training of Volunteers for PPAF project baseline | bar: 21 to 26
School Baseline survey and HH survey of PPAF project | bar: 27 to 30
TVET | MC Programme Implementation/Loan disbursement in 3 districts | bar: 1 to 15
Submission of EOI skill for market 2014-15 to PSDF | bar: 25 to 29
Finalization of MOU TEVTA | bar: 1 to 5; 25 to 30
Registration of training Venues with TEVTA
Community mobilization and admission campaign for SSPG | bar: 8 to 30
Opening of 8 new centers of SSPG | bar: 8 to 30
Local agreements on new trades with education institutions in Punjab
Guddi Baji programme implementation
School 4 Life/ASK | Orientation Sessions With School Management | bar: 18 to 19; 24
World Health Day | bar: 14
Orientation Sessions With School Management and Faculty | bar: 19; 23
Heart Connection Tours | bar: 22 to 26; 29 to 30
Inter-Universities Drama Competition | bar: 29 to 30
RTE | World at School-Global Youth Ambassador (National/Provinces) Ongoing (April 2014-March 2015)
RTE Press Conference on 25A | bar: 18
Celebration of 4th Anniversary of 25 A | bar: 19
Provincial Consultation Meeting on Article 25 A, Right to Education-Quetta - Baluchistan | bar: 25
CLF | School based CLF in Sahiwal | bar: 19
Associated CLF in Islamabad as part of National Book Reading Week in Islamabad | bar: 22 to 24
IPL Pre Service | A session with Prof. Shaheen Sardar Ali on her " Latest Research Areas on Gender and Justice" | bar: 7
IPL Classes
ToT, Musa Khail Baluchistan- L4A and Focus Group Discussion under PPAF | bar: 9 to 11; 14 to 17
IPL | ToT, Sukkur Sindh - Project Orientation, MEAL, L4A, TWF, ECE & WSIP under DC Project Phase-III | bar: 14 to 25
In-service | Revision of Primary Level Reading Kit | bar: 6 to 18
Other | ITA Strategic Planning Meeting | bar: 2 to 4
Programme Director Baela Raza Jamil is attending the SANKALP Unconventional Summit in Mumbai Panel: Focus on South Asia: Capital Flows Are Not Enough: Missing Ingredients for Building Venture Ecosystems in South Asia | bar: 10 to 12
World Bank's SABER Project team meeting with ITA | bar: 17
World Book and Copyright Day | bar: 23
E- Newsletter
Low Cost School Conference - LUMS | bar: 22 to 23

## May 2014
Idara-e-Taleem-o-Aaghai (ITA)
Quarterly Planner (April to June)
2014-05-01
Program/ Project | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SASI Marketing and Improvement Partnership
SASI Trend Analysis Report
SASI Market Research | bar: 1 to 15
ASER | Baithaks in RYK (Chak 88-P,Chak 31-P,Gehna Larr, Chak 145-P,Chak 224-P) | bar: 2; 5; 16; 21
Baithaks in Multan (Tarf Mubarik Doim,Qasba Sani,Neel Kot B, Neel kot A,Nawab Pur Awal, Muzaffarabad,Mubarikpur,Jahangirabad,Chah Gehnay Wala,Alamdi Sura) | bar: 3; 6 to 7; 15; 22 to 25; 30 to 31
Baithaks in Rawalpindi ( Gerosi Gujar Khan,Kurnali Gujar khan,Narali Gujar Khan,Thoha Khalsa Kahota,Panyali Kahota,Bishandot Kallar Saydan,Ausia Murree,Usman Khattar Texilla,Nambal Murree,Chohan Rawalpindi) | bar: 19 to 24; 26 to 28
Baithaks in Mianwali (Ban Sumbal, Khola, NooruAllahwala, Tarag, Wata Khail) | bar: 8 to 9; 11
Baithaks in Khushab (GHSS Khushab,Oklimohla,Utra,Bijar,Adhikot,Roda) | bar: 3; 5 to 7
Baithaks in Faisalabad (46JB,217 RB,222 RB,251 RB,Killianwala,63GB,240GB,353GB, Hasokay GB) | bar: 6; 10; 12; 14; 17; 20; 22 to 24
Baithaks in Chiniot ( Bagh Shah Behlol,Bahiwal,Bukharian,Chak 126,Chak146,Chak 201,Chak 243,Mouza Balhar Ka,Mouza Suleman,Thatta Mian Lala) | bar: 9 to 10; 12 to 17; 19
Baithaks in DG Khan (Basti Malana, Shah Sadar din) | bar: 27 to 28
District Launch Dera Ghazi Khan | bar: 9
Baithaks in Muzaffar Garh ( Qlanar wala, Khar Gharbi, Chak 519-TDA, Chak 532-TDA,Dolat Pur,Pattal Kot Addu,Gajvian,Kacha Kinjar,Khan Pur shumali,Patti Ghulam Ali) | bar: 6 to 8; 11; 14 to 15; 30
Dialogue on Right to Education (RTE) Article 25- A Learning Challenges and Inclusion of All | bar: 5
Coalition Meeting | bar: 19; 23
ECE | ECE Training to WSIP Schools Lahore | bar: 6 to 7
School Baseline survey to identify ECE status in target in UCs
ECE teachers identification | bar: 16 to 30
Identification of ECD Day care centers in Musa Khail | bar: 1 to 7
WSIP | Trainings of Volunteers for DC + Baseline survey (Schools & HH) | bar: 15 to 30
Identification of volunteers in Multan for Baseline under Oxfam GB project | bar: 23 to 24
School Baseline survey & HH survey in UC Jakhar Pur | bar: 25 to 31
Report cards of HH survey for PPAF | bar: 1 to 11
TVET | Guddi Baji operations in Punjab (Ongoing)
PSDF proposal for 2 districts skills for market 2014-15 (Ongoing)
PSDF proposal for 2 districts skills for Jobs 2014-15 (Ongoing)
School 4 Life/ASK | Orientation Sessions With School Faculty | bar: 5 to 8
Heart Connection Tours
Peer Educators Awareness Sessions | bar: 14 to 31
Informal Session on SRHR | bar: 20 to 21; 29 to 30
Mother's day celebration | bar: 10
RTE | Global Action Week | bar: 4 to 10
Seminar and Policy discussion on Early Childhood Education
Journalist Awards
Dialogue on Right to Education Article 25-A Learning Challenges and Inclusion of All | bar: 5
Provincial Consultation Meeting on Article 25 A, Right to Education - Peshawar,KPK | bar: 13
Provincial Consultation Meeting on Article 25 A, Right to Education -Karachi, Sindh | bar: 8
CLF | Teachers' Literature Festival in Islamabad. | bar: 1
Mega CLF in Islamabad at the Federal College of Education | bar: 2 to 3
IPL Pre Service | IPL Board Meeting | bar: 9
Classes
Exams | bar: 26 to 30
IPL In-service | Site Support Visit to WSIP Schools Lahore | bar: 13 to 15; 20 to 21
Material Development-TLMs | bar: 18 to 24
ECE Training to WSIP Schools Lahore | bar: 6 to 7
ITA board Meeting | bar: 10
ITA Strategic Planning Meeting | bar: 25 to 31
Baela Raza Jamil attended a Global Education for All Meeting | bar: 12 to 14

## June 2014
Idara-e-Taleem-o-Aaghai (ITA)
Quarterly Planner (April to June)
2014-06-01
Program/ Project | Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
SASI | Initiation of partnership with Khushaal School under Malala Fund
NISA Alliance Pakistan chapter initiation | bar: 1 to 7
SASI toolkit development and revision
Collaboration with SWAaT for Pakistan (school assessments) | bar: 8 to 14
Finalization of Parnership with JCR-VIS for School rating programme | bar: 10 to 30
Formulation of acreditaion panel for School ratong prpgramme | bar: 23 to 30
School Improvement Partnerships
ASER | Baithak in DG Khan (Paigan) | bar: 2
District Launch Tendo M. Khan | bar: 24
District Launch Mir Pur Khas | bar: 25
District Launch Jacobabad | bar: 27
ASER Brochure (E) Printed
ECE | Furniture provisions to ECD Daycare centres in Musa Khail | bar: 9
ECE Kit provisions to Musa Khail | bar: 1 to 2
Physical need assessment of ECD centers + BOQs + Tenders + Work order repair work | bar: 9 to 30
Enrolling children in the ECD Centers | bar: 16 to 21; 23 to 29
Data entry of baseline findings on ECE components under DC project
ECE teachers identification
Enlisting ECE teachers of Public/Private Schools for TOTs | bar: 9 to 14
Interviews and tests to identify potential teachers as master trainer in Sukkhar and Shikarpur | bar: 16 to 21
Planning and coordination with concerning authorities for TOTs | bar: 23 to 29
WSIP | Data Entry of baseline survey & HH survey DC project | bar: 1 to 7
Data Entry of baseline survey & HH survey DC project Multan (Oxfam GB) | bar: 1 to 7
ASER Bathiks in DC target villages | bar: 9 to 30
Formation of Village Education Committee & selection of volunteers/ Para teachers | bar: 9 to 30
Meeting with Department (Edu.) about household survey | bar: 16 to 21
Signing of MOUs with District Government | bar: 9 to 15
Dubai Care | DC brochure (E) printed
TVET | Program Monitoring Visits in all TVET Districts (Selection of new team members as well)
Achieved GB Project 2014 (Selection of Team Members with HR)
Project Orientation GB2014 with new district coordinators | bar: 14 to 19
Achieved PSDF Project 2014-15
PSDF Project Planning Meeting with relevant districts | bar: 23 to 30
Micro Credit Distribution Ceremony Muzaffarghar/Chiniot | bar: 17; 24
Linkages with Garments Industries in Faisalabad district | bar: 1 to 6
Initiate Sanjan Nagar TVET Programme initially with 2 trades | bar: 15 to 30
SSPG Programme Updation | bar: 10 to 19
Training Material Development with Qaser-e-Bhabood | bar: 1 to 15
Linkages of Model Village Students with Kalash Garments Industry
School 4 Life/ASK | Heart Connection Tours
Peer Educators Awareness Sessions | bar: 1 to 15
Informal Session on SRHR | bar: 9 to 22
Teacher trainings | bar: 16 to 18
Roundtable conference on Father's Day | bar: 17
Two day South Asian Right to Education & ECED meeting in Karachi (CENCELLED) | bar: 5 to 6
CLF | Dates are not decided yet but we are planning to hold a school based CLF in Swat
IPL Pre service | Orientation Seminar on IPL | bar: 4
IPL Classes
Admission Campaign (Ongoing)-Sep
IPL social week | bar: 9 to 13
Preparation of Academic week | bar: 16 to 20
IPL In-service | ToT on CAMaL Methodology BY partner organization Paratham India under DC Project | bar: 2 to 10
TOT on Adult Literacy by JICA under DC Project | bar: 11 to 13
Others | Panel discussion: Activism for Education: Bridging Gaps in Demand and Supply of Education - Baela Raza Jamil was the panelist with Dr. Javed Awan (District Education Officer, Gujranwala), Imran Khan( Campaign Manager Civil Society -Alif Ailaan), Muhammad Inam (District Education Officer, Noshera) and Muhammad Ansar Kamal (District Monitoring officer) | bar: 5
A roundtable discussion on Citizens of tomorrow: Sharing experiences in Education from the grass Roots at University of Warwick With Monazza Aslam, Baela Jamil and Shaheen Ali | bar: 11
A roundtable discussion on Citizens re-shaping education through evidence-based annual learning accountability initiatives in Pakistan and beyond with Monazza Aslam, Baela Jamil, and Pauline Rose, Professor of International Education, University of Cambridge | bar: 12
ITA brochure (E) printed