## Card
Children, Especially Girls Aged 2-12 Have Access To Quality Education With Improved Infrastructure And Safe Learning Environment
Project Implemented by Idara-e-Taleem-o-Aagahi (ITA) in collaboration with Dubai Cares and School Education Department from April 2011 till June 2013
SCHOOL ACCOUNTABILITY CARD
This Card is jointly filled by School Head & ITA Representative
School Name |  | EMIS Code | Tehsil | District
GPS Ghari canal colony |  | 32320136 | Kot Addu | Muzaffargarh
Enrolment |  | No. of Teachers |  | No. of School Council Members
Boys | Girls | Govt. | Para | Male | Female
206 | 13 | 6 | 0 | 7
WORK/ACTIVITY DONE |  | DETAIL / STATUS | COST (Rs.) | COMMENTS / SUGGESTIONS
1. SCHOOL INFRASTRUCTURE
Summary of Construction Work Done |  | One New Classroom√
New Toilet Block with Saptic Tank√
Electric Work
Sanitary work
Repair work
2. SCHOOL FURNITURE
ECE Chairs |  | 0 | 0
ECE Tables |  | 0 | 0
Bench & Desk |  | 0 | 0
Teacher Chair |  | 0 | 0
Teacher Table |  | 0 | 0
White Board |  | 0 | 0
Soft Board |  | 0 | 0
Steal Almirah |  | 0 | 0
Signboard |  | 0 | 0
School Inaugration |  | 0 | 0
Sub Total-2 |  |  | 0
3. TEACHING LEARNING MATERIALS (TLMs)
ECE Kit |  | YES | 5000
Primary Science Kit |  | No | 0
Primary Reading Kit with maps and globes |  | YES | 12000
Health Kit including First Aid Box |  | YES | 6150
Sports Kit |  | YES | 3200
Sub Total-3 |  |  | 26350
4. HUMAN RESOURCE MANAGEMENT & DEVELOPMENT
Para Teacher/s |  | 01 hired since June 2012 till May 2013 @ Rs. 2500 p.m. | 0
List of Trainings conducted for Head Teacher/Teachers |  | a) 12 day training for on ECE, H&H, Subject Based - 02 teachers trained | 14160
|  | b) 03 day training for on TLMs - 02 teachers trained | 3540
|  | c) 03 day refresher training for 02 teachers | 3540
|  | d) 03 day training on Annual School Planning, ECE for 02 teachers | 3540
School Council |  | 04 day SC training - 02 SC members trained | 4720
Construction Committee |  | 01 day training of 03 CC members | 600
Sub Total-4 |  |  | 30100
5. BACK-TO-SCHOOL-KITS
School Bag & Stationery Items |  | For 100 students | 0
Uniform & School Shoes |  | For 100 students | 0
Sweaters |  | For 100 students | 0
Sub Total-5 |  |  | 0
6. CHILD DEVELOPMENT
Monthly Art Material for Students (Colors, Charts, Markers, Glue, etc) |  | For 06 months @ Rs. 425 per month | 2550 | It should be continued; students are very happy with drawings & paints
Monthly Art Fund for Student for 06 months |  | For 06 months @ Rs. 425 per month | 2500 | In SC/SMC Account
Summer Camp |  | 3 weeks program - 25 students attended | 10000 | Stationery, Ice for cold water, etc
Health / hygiene activities |  | HPM sessions | 10000 | 05 students & 01 teacher
Litercay Camps (Hiring of Volunteer, Reading Material, etc) |  | 30 days program | 7000 | 29 girls students
Children's Lit Festival 2013 |  | Yes | 6000 | 2 students and 01 teacher
Children's theatre |  | No
Activism events |  | No
Sub Total-6 |  |  | 38050
7. STUDENTS' CLUB (Boys' Club / Girls' Club)
Girl Clubs formation(student club) |  | Yes | 1500 | 5 Students as members
Sashes |  | Yes | 1000 | 5 Students as members
Badges |  | YES (for club member and focal teacher) | 100 | 5 Students as members
Sub Total-7 |  |  | 2600
8. CELEBRATION OF ADVOCACY DAYS (NATIONAL / INTERNATIONAL)
Women's Day |  | No | 0
EFA Week- April |  | Yes | 1500
14th Aug/Indep Day |  | No | 0
Literacy Day Sept |  | Yes | 1000
World Teachers' Day Oct. |  | No | 0
Child Rights Day Nov. |  | No | 0
Malala Day / November |  | Yes | 1000
Signing 01 Million Signature Petition (2012 & 2013) |  | Yes | 1000
Sub Total-8 |  |  | 4500
Grand Total |  |  | 101600
For any suggestions / complaints please contact the following officials
Name |  | Designation | Tel # | Cell #
Ahsan ul Allah |  | Head Teacher |  | 3458780383
Sohaib Imran |  | EDO (Education) Muzafargarh |  | 3009639318
Mr. Amjad Imtiaz |  | Program Manager, ITA | 042-3517005-6 | 0321-4031855
Visits/Verification by: Name/Designation during 2013:
1
2
3
4
5
(use extra page if needed)