## STREET
DASTAK Plan of Advocacy Campaign on MHM from - September 2024
S# | Activity | Content Type/ | No. of activities | Mode | Timeline
[5 empty] | 1st week | 2nd Week | 3rd Week | 4th Week
1 | MHM Workshops | 1.1 MHM Workshops in Lahore. | 1 | In person | Sessions |  |  | Reporting
|  | 1.2 MHM Workshop in Karachi | 3
|  | 1.2 MHM Workshop in Gujaranwala. | 1
|  | 1.3 MHM Workshop in Skardu | 1
|  | 1.6 MHM Workshop in Jamshoro | 1
|  | 1.7 MHM Workshop in Ghizer | 1
|  | Awareness raising sessions on MHM with young girls at school and community level | Total 10
2 | Peer Education Program | Young girls will be selected as peer educators from within the MHM workshops | 1 | In person |  |  |  | Reporting
3 | Research Brief on MHM myths and taboos | A research brief of myths and taboos related to MHM will be developed, the data will be collected during the MHM sessions being organized | 1 |  |  |  |  | Reporting
4 | Social Media Campaign Cross-cutting | Cross-cutting social media campaign |  | Virtual