## STREET
STREET Plan of Advocacy Campaign on MHM from July-August 2024
S# | Activity | Content Type | No. of activities | Mode
[5 empty] | 2nd Week | 3rd Week | 4th Week
1 | Research Paper | Development of Research Paper on Adolescents Health Issues and MHM | 1 | In person | Data Collection | Analysis of data | Final report
2 | Awareness & sensitization sessions with adolescents & youth in communitites & educational institutes | Senstizing and empowering youth & advolescents on health & hygiene with specific focus on MHM | 3 | In person | 1 session | 1 session | 1 session
3 | Establishment of MHM leads | Establishment & formation of MHM leads in schools who will be leading MHM senstization sessions in their institutes & communities within and beyond the project life (25 MHM leads) Rizwana will lead this process | 1 | In person | Formation of MHM Leads
4 | Planning and implemintation of MHM actions | MHM leads will plan and implement innovative MHM actions in their institutes & communities | 3 | In person | 1 MHM Action by MHM Leads | 1 MHM Action by MHM Leads | 1 MHM Action by MHM Leads
5 | Radio Show | Stakeholders & experts senstizing urban & rural communitiestalking on health & hygiene and MHM | 2 | Radio show |  | 1 Radio Show | 1 Radio Show
Total Campaign Cost |  |  |  | #REF!